## Dashboard
IOM PLAN VS ACHIEVED — FY 2026–27
Period | YTD |  | MTD | August 2026
From |  |  | Units | ₹ crore, excluding tax
To | 2026-08-31 |  | Calculation | Automatic when source tabs are updated
Management Summary
Plan / Budget |  | Achieved Awards |  | Achievement
Category | Plan / Budget | Achieved | Count | Achievement %
Awarded IOM
Procurement
Balance |  | 0 |  | 0
Overall
TES / Non-TES Awards
Classification | Plan / Budget | Achieved | Achievement %
TES
Non-TES
Overall awards include records where TES / Non-TES is not filled.
BOQ and Design Dependencies — Overall Balance
Team | Dependency | Planned Awards | Recorded PTE
C&B | BOQ
Design | BOQ
Design | Drawing
Monthly Plan vs Achieved
Month | Plan / Budget | Achieved | Balance PTE
2026-04-01
2026-05-01
2026-06-01
2026-07-01
2026-08-01
2026-09-01
2026-10-01
2026-11-01
2026-12-01
2027-01-01
2027-02-01
2027-03-01
Calculation basis
Plan = unique awarded-IOM budget + unique procurement-IOM budget + recorded PTE for balance work scheduled in the selected period.
Achieved = unique contract award value + unique procurement award value. Multi-vendor procurement IOMs are counted once.
Update values in Contracts, Procurement or Balance tabs. Blank values are excluded and begin contributing automatically when filled.
Formulas:
MTD = SUMIFS(Balance!$F2:F10000,Balance!$E2:E10000,">="&[Period],Balance!$E2:E10000,"<="&EOMONTH([Period],0))

## Contracts
IOM Version | Project | Package | Awarded Vendor | TES / Non-TES | Requisition Date | Award Date | Unique Flag | Budget (₹ Cr) | Unique Award (₹ Cr)
IOMC20260425052514 | Godrej Joka | Civil - General | Ada Metcon | TES | 2026-04-23 | 2026-04-26 | 1 | 0.387 | 0.322
IOMC20260425063240 | Godrej Joka | Miscellaneous / other | Indicative Consultant India | Non-TES | 2026-04-23 | 2026-04-26 | 1 | 0.018 | 0.01374
IOMC20260512064130 | Godrej Joka | Finishing - Painting | Maa Tara Enterprise | TES | 2026-04-16 | 2026-05-13 | 1 | 1.35 | 2.228
IOMC20260512064130 | Godrej Joka | Finishing - Painting | MOZAMMEL SEKH | TES | 2026-04-16 | 2026-05-13 | 0 | 1.35 | 0
IOMC20260520065412 | Godrej Joka | Miscellaneous / other | JRS CONSTRUCTION | Non-TES | 2026-04-17 | 2026-05-21 | 1 | 0.213 | 0.196
IOMC20260529050740 | Godrej Joka | Miscellaneous | VISHAL JAISWAL | Non-TES | 2026-05-27 | 2026-05-30 | 1 | 0.2175 | 0.2175
IOMC20260529051614 | Godrej Joka | Miscellaneous | KISHAN JAISWAL | Non-TES | 2026-05-27 | 2026-05-30 | 1 | 0.2175 | 0.2175
IOMC20260603012523 | Godrej Joka | Miscellaneous | VISHAL JAISWAL | Non-TES | 2026-05-27 | 2026-06-04 | 1 | 0.23925 | 0.23925
IOMC20260603013034 | Godrej Joka | Miscellaneous | KISHAN JAISWAL | Non-TES | 2026-05-27 | 2026-06-04 | 1 | 0.23925 | 0.23925
IOMC20260613063044 | Godrej Joka | Civil - Water Proofing and Expansion Joints | PURVYAKRUTI SALES & SERVICES PRIVATE LIMITED | TES | 2026-05-27 | 2026-06-14 | 1 | 1.488 | 3.569
IOMC20260613063044 | Godrej Joka | Civil - Water Proofing and Expansion Joints | JSS ENGINEERING PRIVATE LIMITED | TES | 2026-05-27 | 2026-06-14 | 0 | 2.232 | 0
IOMC20260624011203 | Godrej Joka | Miscellaneous | RABI CONSTRUCTION | Non-TES | 2026-06-20 | 2026-06-25 | 1 | 0.0058 | 0.0045
IOMC20260624024943 | Godrej Joka | Miscellaneous | SANITECH INFRASTRUCTURES PVT LTD | Non-TES | 2026-06-20 | 2026-06-25 | 1 | 0.0232 | 0.0108
IOMC20260626065311 | Godrej Joka | Miscellaneous | ZOYA ENGINEERING & CONSTRUCTION COMPANY | Non-TES | 2026-06-25 | 2026-06-27 | 1 | 0.0335 | 0.0315
IOMC20260702013921 | Godrej Joka | Finishing - Al Windows/UPVC | HINDUSTAN ALUMINIUM WORKS | TES | 2026-06-25 | 2026-07-03 | 1 | 2.725 | 5.567
IOMC20260702013921 | Godrej Joka | Finishing - Al Windows/UPVC | ALUCOM | TES | 2026-06-25 | 2026-07-03 | 0 | 2.885 | 0
IOMC20260708082730 | Godrej Joka | Miscellaneous | ZOYA ENGINEERING & CONSTRUCTION COMPANY | Non-TES | 2024-07-08 | 2026-07-09 | 1 | 0.004 | 0.0031
IOMC20260721210317 | Godrej Joka | Miscellaneous | Aline Curtain walls Pvt Ltd | Non-TES | 2026-07-03 | 2026-07-22 | 1 | 0.0098 | 0.0097
IOMC20260722161546 | Godrej Joka | Supply of safety equipment | Rishikesh Enterprise | Non-TES | 2026-07-17 | 2026-07-23 | 1 | 0.0066 | 0.0043
IOMC20260727195945 | Godrej Joka | Miscellaneous | Sanitary Syndicate Pvt Ltd | Non-TES | 2026-07-24 | 2026-07-28 | 1 | 0.0038 | 0.0027
IOMC20260729182021 | Godrej Joka | MEP - OWC | 3R URBAN SOLUTIONS PVT LTD | TES | 2026-06-18 | 2026-07-30 | 1 | 0.081 | 0.0623
IOMC20260826172513 | Godrej Joka | Miscellaneous | ROY ENGINEERING | Non-TES | 2026-08-25 | 2026-08-27 | 1 | 0.0619 | 0.0619
IOMC20260826175713 | Godrej Joka | Miscellaneous | Pioneer Coop Engineers and Construction | Non-TES | 2026-08-25 | 2026-08-27 | 1 | 0.012 | 0.012
IOMC20260828200004 | Godrej Joka | Miscellaneous / other | C&B Ecogen Private Limited | Non-TES | 2026-08-19 | 2026-08-29 | 1 | 0.0178 | 0.0166
IOMC20260409054741 | Godrej Prakriti | Finishing - Door/Fire Door | Shreeji Woodcraft Pvt Ltd | Non-TES | 2026-03-25 | 2026-04-10 | 1 | 0.0179 | 0.0174
IOMC20260420121908 | Godrej Prakriti | Finishing - Painting | BIBHAS KUMAR DUTTA | Non-TES | 2026-03-18 | 2026-04-21 | 1 | 0.1516 | 0.1138
IOMC20260420121908 | Godrej Prakriti | Finishing - Painting | MOZAMMEL SEKH | Non-TES | 2026-03-18 | 2026-04-21 | 0 | 0.0351 | 0
IOMC20260501044941 | Godrej Prakriti | Civil - General | SGK INFRA ARCHITECTURE CO | Non-TES | 2026-03-05 | 2026-05-02 | 1 | 0.107 | 0.066
IOMC20260505120640 | Godrej Prakriti | MEP - Electrical | RSM PROJECTS & ENGINEERS PRIVATE LIMITED | Non-TES | 2026-04-28 | 2026-05-06 | 1 | 0.15 | 0.121
IOMC20260517010102 | Godrej Prakriti | Minor civil & finishing works | Innovative Vastunirman Private Limited | Non-TES | 2026-04-16 | 2026-05-18 | 1 | 0.01 | 0.01
IOMC20260613113646 | Godrej Prakriti | Minor civil & finishing works | J D ELECTRICAL ENGINEERING SERVICES PRIVATE LIMITED | Non-TES | 2026-06-08 | 2026-06-14 | 1 | 0.0255 | 0.0255
IOMC20260614010940 | Godrej Prakriti | Minor civil & finishing works | VEDASHREE ENTERPRISES | Non-TES | 2026-05-28 | 2026-06-15 | 1 | 0.076 | 0.076
IOMC20260618072212 | Godrej Prakriti | Miscellaneous | HILTI INDIA PRIVATE LIMITED | Non-TES | 2026-06-16 | 2026-06-19 | 1 | 0.0223 | 0.0223
IOMC20260629044605 | Godrej Prakriti | Finishing - Al Windows/UPVC | HINDUSTAN ALUMINIUM WORKS | Non-TES | 2026-06-23 | 2026-06-30 | 1 | 0.301 | 0.287
IOMC20260630114345 | Godrej Prakriti | Supply of labour | VEDASHREE ENTERPRISES | Non-TES | 2026-06-24 | 2026-07-01 | 1 | 0.2294 | 0.2294
IOMC20260701115430 | Godrej Prakriti | Civil - General | B S Enterprise | Non-TES | 2026-06-22 | 2026-07-02 | 1 | 0.415 | 0.378
IOMC20260701011759 | Godrej Prakriti | Civil - General | B S Enterprise | Non-TES | 2026-06-17 | 2026-07-02 | 1 | 0.1395 | 0.1345
IOMC20260707023323 | Godrej Prakriti | Minor civil & finishing works | SUDHIR KUMAR DHIRAJ KUMAR | Non-TES | 2026-06-22 | 2026-07-08 | 1 | 0.04 | 0.032
IOMC20260714115139 | Godrej Prakriti | Miscellaneous | Geotest Engineers Pvt Ltd | Non-TES | 2026-07-10 | 2026-07-15 | 1 | 0.0022 | 0.0015
IOMC20260714121409 | Godrej Prakriti | Miscellaneous | SANITECH INFRASTRUCTURES PVT LTD | Non-TES | 2026-06-20 | 2026-07-15 | 1 | 0.035 | 0.025
IOMC20260722171225 | Godrej Prakriti | Miscellaneous | ANTWORT PEST CONTROL | Non-TES | 2026-07-11 | 2026-07-23 | 1 | 0.011 | 0.009
IOMC20260727121112 | Godrej Prakriti | Miscellaneous | Earth Care Products And Services | Non-TES | 2026-07-07 | 2026-07-28 | 1 | 0.015 | 0.0125
IOMC20260803222705 | Godrej Prakriti | Miscellaneous | ADIX SAFETY SOLUTIONS | Non-TES | 2026-08-03 | 2026-08-04 | 1 | 0.02 | 0.0166
IOMC20260816021235 | Godrej Prakriti | Civil - General | BIBHAS KUMAR DUTTA | Non-TES | 2026-07-31 | 2026-08-17 | 1 | 0.551 | 0.548
IOMC20260817200016 | Godrej Prakriti | Miscellaneous | PANDA AND ASSOCIATES | Non-TES | 2026-08-14 | 2026-08-18 | 1 | 0.004 | 0.004
IOMC20260401040346 | B L saha | MEP - Plumbing | Jagrati Civil Constructions Pvt. Ltd. | TES | 2026-03-17 | 2026-04-16 | 1 | 2.514 | 2.445
IOMC20260414064050 | B L saha | MEP - Plumbing | RANA | Non-TES | 2026-03-24 | 2026-04-15 | 1 | 0.0038 | 0.0033
IOMC20260423102610 | B L saha | Finishing - General | BUILDON PLASTERS PRIVATE LIMITED | TES | 2026-02-10 | 2026-04-24 | 1 | 5.056 | 7.022
IOMC20260423102610 | B L saha | Finishing - General | Purkait Enterprise | TES | 2026-02-10 | 2026-04-24 | 0 | 2.257 | 0
IOMC20260425104438 | B L saha | MEP - Plumbing | FIRE GUARD SYNDICATE | TES | 2026-03-16 | 2026-04-26 | 1 | 3.689 | 6.739
IOMC20260425104438 | B L saha | MEP - Plumbing | Sanitech Infrastructures Pvt Ltd | TES | 2026-03-16 | 2026-04-26 | 0 | 3.261 | 0
IOMC20260505114547 | B L saha | Civil - General | SUDHIR KUMAR DHIRAJ KUMAR | Non-TES | 2026-04-17 | 2026-05-06 | 1 | 0.3072 | 0.289
IOMC20260519051210 | B L saha | MEP - Firefighting | SIBAM ENGINEERING PRIVATE LIMITED | TES | 2026-03-02 | 2026-05-20 | 1 | 2.9538 | 5.852
IOMC20260519051210 | B L saha | MEP - Firefighting | Sanitary Syndicate Pvt Ltd | TES | 2026-03-02 | 2026-05-20 | 0 | 2.8982 | 0
IOMC20260601080416 | B L saha | MEP - Electrical | Chakraborty Electricals Pvt Ltd | Non-TES | 2026-05-22 | 2026-06-02 | 1 | 0.0504 | 0.0489
IOMC20260623015323 | B L saha | Miscellaneous | Niyati Enterprises | Non-TES | 2026-06-19 | 2026-06-24 | 1 | 0.0244 | 0.0173
IOMC20260626031812 | B L saha | Miscellaneous | ROY ENGINEERING | Non-TES | 2026-06-19 | 2026-06-27 | 1 | 0.0244 | 0.0175
IOMC20260702115056 | B L saha | Miscellaneous | AVANTECH ENGINEERING CONSORTIUM PVT. LTD. | Non-TES | 2026-07-01 | 2026-07-03 | 1 | 0.045 | 0.044
IOMC20260707033416 | B L saha | Miscellaneous | GREEN VIEW | Non-TES | 2026-07-03 | 2026-07-08 | 1 | 0.00354 | 0.003
IOMC20260723125235 | B L saha | Supply of safety equipment | Rishikesh Enterprise | Non-TES | 2026-07-21 | 2026-07-24 | 1 | 0.004 | 0.0072
IOMC20260723125235 | B L saha | Supply of safety equipment | JAIN SAFEWELD PRIVATE LIMITED | Non-TES | 2026-07-21 | 2026-07-24 | 0 | 0.0047 | 0
IOMC20260803170334 | B L saha | Finishing - General | M/S PACIFIC ENGINEERS | TES | 2026-04-11 | 2026-08-04 | 1 | 12.18 | 27.07
IOMC20260803170334 | B L saha | Finishing - General | Jyoti Tiles LLP | TES | 2026-04-11 | 2026-08-04 | 0 | 16.33 | 0
IOMC20260806231537 | B L saha | Miscellaneous | Walter P Moore | Non-TES | 2026-08-06 | 2026-08-07 | 1 | 0.003 | 0.003
IOMC20260814184540 | B L saha | Miscellaneous | ZOYA ENGINEERING & CONSTRUCTION COMPANY | Non-TES | 2026-08-12 | 2026-08-15 | 1 | 0.0193 | 0.0179
IOMC20260820145119 | B L saha | Miscellaneous | G S Automation |  | 2026-08-04 | 2026-08-21 | 1 | 0.1152 | 0.1104
IOMC20260827161019 | B L saha | MEP - Lifts | Schindler India Pvt. Ltd. |  | 2026-04-23 | 2026-08-28 | 1 | 7.74 | 6.91
IOMC20260827201049 | B L saha | MEP - Plumbing | SANITECH INFRASTRUCTURES PVT LTD |  | 2026-08-07 | 2026-08-28 | 1 | 0.0467 | 0.0366
IOMC20260331125218 | Godrej Ushti 1 | Miscellaneous | P.T.Enterprise | Non-TES | 2026-03-18 | 2026-04-01 | 1 | 0.0044 | 0.0044
IOMC20260420111543 | Godrej Ushti 1 | Miscellaneous / other | Loyalie It Solutions Pvt Ltd | Non-TES | 2026-04-20 | 2026-04-21 | 1 | 0.0253 | 0.0253
IOMC20260422104844 | Godrej Ushti 1 | MOSA infrastructure work | GREEN VIEW | Non-TES | 2026-04-14 | 2026-04-23 | 1 | 0.013 | 0.0124
IOMC20260504065517 | Godrej Ushti 1 | Civil - General | M&M Foundation | TES | 2026-03-27 | 2026-05-05 | 1 | 1.6445 | 1.6002
IOMC20260508120852 | Godrej Ushti 1 | Civil - General | SUDHIR KUMAR DHIRAJ KUMAR | TES | 2026-05-01 | 2026-05-09 | 1 | 0.2999 | 0.2886
IOMC20260519103610 | Godrej Ushti 1 | MEP - Electrical | B.R.CONSTRUCTION | TES | 2026-03-19 | 2026-05-20 | 1 | 0.249 | 0.2311
IOMC20260527035005 | Godrej Ushti 1 | Civil - General | SGK INFRA ARCHITECTURE CO | TES | 2026-05-01 | 2026-05-28 | 1 | 0.7136 | 0.6759
IOMC20260609060953 | Godrej Ushti 1 | Supply of material | SOOR NEOGI COOMAR & CO. PVT. LTD. | Non-TES | 2026-06-04 | 2026-06-10 | 1 | 0.1381 | 0.1381
IOMC20260609080222 | Godrej Ushti 1 | Supply of material | PAVE INDIA ENTERPRISE | Non-TES | 2026-06-09 | 2026-06-10 | 1 | 0.0644 | 0.0644
IOMC20260618023626 | Godrej Ushti 1 | Housekeeping, site office, temporary office | Sudhir Kumar Dhiraj Kumar | Non-TES | 2026-06-10 | 2026-06-19 | 1 | 0.0825 | 0.0781
IOMC20260618041029 | Godrej Ushti 1 | Infrastructure - Sinages | A K Enterprise | TES | 2026-05-20 | 2026-06-19 | 1 | 0.2801 | 0.2606
IOMC20260629040050 | Godrej Ushti 1 | MEP - Electrical | RSM PROJECTS & ENGINEERS PRIVATE LIMITED | TES | 2026-05-31 | 2026-06-30 | 1 | 0.2239 | 0.1072
IOMC20260716115425 | Godrej Ushti 1 | MOSA infrastructure work | GREEN VIEW | TES | 2026-07-13 | 2026-07-17 | 1 | 0.07 | 0.07
IOMC20260716190154 | Godrej Ushti 1 | Miscellaneous | SANITECH INFRASTRUCTURES PVT LTD | Non-TES | 2026-07-01 | 2026-07-17 | 1 | 0.0017 | 0.0017
IOMC20260727200221 | Godrej Ushti 1 | MEP - OWC | 3R URBAN SOLUTIONS PVT LTD | TES | 2026-08-22 | 2026-08-28 | 1 | 0.094 | 0.0686
IOMC20260728134902 | Godrej Ushti 1 | Finishing - Al Windows/UPVC | HINDUSTAN ALUMINIUM WORKS | TES | 2026-08-03 | 2026-08-29 | 1 | 0.0242 | 0.0182
IOMC20260729185013 | Godrej Ushti 1 | MEP - Plumbing | Sanitech Infrastructures Pvt Ltd | TES | 2026-08-01 | 2026-08-30 | 1 | 0.4447 | 0.3963
IOMC20260730204038 | Godrej Ushti 1 | Supply of material | Durga Pipes | Non-TES | 2026-07-27 | 2026-07-31 | 1 | 0.0612 | 0.0612
IOMC20260805204041 | Godrej Ushti 1 | Supply of material | Durga Pipes | Non-TES | 2026-08-03 | 2026-08-06 | 1 | 0.1151 | 0.1151
IOMC20260809211106 | Godrej Ushti 1 | Minor civil & finishing works | Khan Enterprise | Non-TES | 2026-07-23 | 2026-08-10 | 1 | 0.0162 | 0.0158
IOMC20260814182846 | Godrej Ushti 1 | Minor civil & finishing works | Khan Enterprise | Non-TES | 2026-07-23 | 2026-08-15 | 1 | 0.0162 | 0.0158
IOMC20260816115058 | Godrej Ushti 1 | Infrastructure - Landscaping/Softscape | Flora International Greenscapes Pvt. Ltd. | Non-TES | 2026-08-12 | 2026-08-17 | 1 | 0.44 | 0.6199
IOMC20260816115058 | Godrej Ushti 1 | Infrastructure - Landscaping/Softscape | ROYAL MICRO IRRIGATION SYSTEMS | Non-TES | 2026-08-12 | 2026-08-17 | 0 | 0.44 | 0
IOMC20260902145936 | Godrej Ushti 1 | Civil - General | ZOYA ENGINEERING & CONSTRUCTION COMPANY |  | 2026-08-27 | 2026-09-03 | 1 | 0.2302 | 0.2244
IOMC20260409041716 | Raipur Plotted 1 | MEP - STP / WTP | PTC WATERTECH LLP |  | 2026-04-03 | 2026-04-10 | 1 | 0.7711 | 0.6951
IOMC20260416064433 | Raipur Plotted 1 | Miscellaneous | PS Enterprises |  | 2026-04-12 | 2026-04-17 | 1 | 0.0069 | 0.0067
IOMC20260416072113 | Raipur Plotted 1 | Miscellaneous | SMS INTEGRATED FACILITY SERVICES PRIVATE LIMITED |  | 2026-04-12 | 2026-04-17 | 1 | 0.0111 | 0.0111
IOMC20260423061721 | Raipur Plotted 1 | MEP - Electrical | Acharya Electrical |  | 2026-04-02 | 2026-04-24 | 1 | 3.8238 | 3.6505
IOMC20260424070952 | Raipur Plotted 1 | Miscellaneous / other | LOYALIE-IT SOLUTIONS PRIVATE LIMITED |  | 2026-04-20 | 2026-04-25 | 1 | 0.0102 | 0.0102
IOMC20260515120423 | Raipur Plotted 1 | Finishing - Painting | Khan Enterprise |  | 2026-05-09 | 2026-05-16 | 1 | 0.0428 | 0.0207
IOMC20260525034756 | Raipur Plotted 1 | Miscellaneous | OMEGA TEST HOUSE PRIVATE LIMITED |  | 2026-05-22 | 2026-05-26 | 1 | 0.0057 | 0.0055
IOMC20260603062823 | Raipur Plotted 1 | Civil - Core & Shell | VINOD KUMAR JAIN |  | 2025-05-04 | 2026-06-04 | 1 | 0.8072 | 0.7857
IOMC20260604064423 | Raipur Plotted 1 | Civil - Core & Shell | VINOD KUMAR JAIN |  | 2026-05-04 | 2026-06-05 | 1 | 0.3928 | 0.3794
IOMC20260607123916 | Raipur Plotted 1 | Civil - Core & Shell | VINOD KUMAR JAIN |  | 2026-05-18 | 2026-06-05 | 1 | 0.3348 | 0.3248
IOMC20260611120616 | Raipur Plotted 1 | Miscellaneous | NITA FIRE SAFETY SOLUTIONS |  | 2026-06-10 | 2026-06-12 | 1 | 0.0059 | 0.0059
IOMC20260629045401 | Raipur Plotted 1 | Civil - Core & Shell | M/s Aulia Infrastructure |  | 2026-03-27 | 2026-06-30 | 1 | 0.28197 | 0.26738
IOMC20260706071758 | Raipur Plotted 1 | Civil - Core & Shell | Aquaplast Infracon Pvt Ltd |  | 2026-06-01 | 2026-06-07 | 1 | 1.3092 | 1.2707
IOMC20260708040525 | Raipur Plotted 1 | Civil - Water Proofing and Expansion Joints | PURVYAKRUTI SALES & SERVICES PRIVATE LIMITED |  | 2026-06-03 | 2026-07-09 | 1 | 0.6084 | 0.595
IOMC20260708042446 | Raipur Plotted 1 | Civil - Core & Shell | M/s Aulia Infrastructure |  | 2026-04-25 | 2026-07-09 | 1 | 2.9744 | 2.884
IOMC20260710120728 | Raipur Plotted 1 | Miscellaneous | ORION PEST SOLUTIONS PRIVATE LIMITED |  | 2026-06-26 | 2026-07-11 | 1 | 0.0059 | 0.0046
IOMC20260710122754 | Raipur Plotted 1 | Miscellaneous | ORION PEST SOLUTIONS PRIVATE LIMITED |  | 2026-06-26 | 2026-07-11 | 1 | 0.0117 | 0.0064
IOMC20260731163015 | Raipur Plotted 1 | MEP - STP / WTP | PTC WATERTECH LLP |  | 2026-07-23 | 2026-08-01 | 1 | 0.2716 | 0.258
IOMC20260813190317 | Raipur Plotted 1 | Housekeeping, site office, temporary office | VINOD KUMAR JAIN |  | 2026-08-11 | 2026-08-14 | 1 | 0.0808 | 0.0783
IOMC20260516112107 | Godrej Nonadanga | Civil - General | SUDHIR KUMAR DHIRAJ KUMAR |  | 2026-05-04 | 2026-05-17 | 1 | 0.4251 | 0.3571

## Procurement
IOM Version | Project | Package | TES / Non-TES | Award Date | Budget (₹ Cr) | Award Value (₹ Cr) | Awarded Count
IOMP20260330110946 | Godrej Joka | Miscellaneous / other works | Non-TES | 2026-03-30 | 0.0147 | 0.0147 | 1
IOMP20260402084753 | Godrej Joka | Civil - RMC | TES | 2026-04-02 | 1.8 | 1.7726 | 1
IOMP20260407041146 | Godrej Joka | Civil - Steel Rebar | TES | 2026-04-07 | 1.041 | 1.0379 | 1
IOMP20260408112501 | Godrej Joka | Civil - RMC | TES | 2026-04-08 | 1.1658 | 1.094 | 1
IOMP20260409085044 | Godrej Joka | Miscellaneous / other works | Non-TES | 2026-04-09 | 0.00766 | 0.00766 | 1
IOMP20260425035921 | Godrej Joka | Miscellaneous / other works | Non-TES | 2026-04-25 | 0.0144 | 0.0144 | 1
IOMP20260425041300 | Godrej Joka | Miscellaneous / other works | Non-TES | 2026-04-25 | 0.0644 | 0.0644 | 1
IOMP20260427103519 | Godrej Joka | Civil - Steel Rebar | TES | 2026-04-27 | 0.7194 | 0.6346 | 1
IOMP20260504043440 | Godrej Joka | Civil - RMC | TES | 2026-05-04 | 0.9609 | 0.9321 | 1
IOMP20260511031924 | Godrej Joka | Civil - Aluminium Formwork |  | 2026-05-11 | 13.63 | 13.41 | 1
IOMP20260515104639 | Godrej Joka | Civil - Steel Rebar | TES | 2026-05-15 | 0.396 | 0.3736 | 1
IOMP20260521062624 | Godrej Joka | Civil - RMC | TES | 2026-05-21 | 0.1192 | 0.1175 | 1
IOMP20260522100422 | Godrej Joka | Civil - RMC | TES | 2026-05-22 | 0.972 | 0.9532 | 1
IOMP20260527110324 | Godrej Joka | Civil - Steel Rebar | TES | 2026-05-27 | 0.198 | 0.1836 | 1
IOMP20260608070120 | Godrej Joka | Civil - RMC | TES | 2026-06-08 | 1.4771 | 1.4134 | 1
IOMP20260618122433 | Godrej Joka | Miscellaneous / other works |  | 2026-06-18 | 0.00728 | 0.00728 | 1
IOMP20260709122844 | Godrej Joka | Civil - Steel Rebar | TES | 2026-07-09 | 1.3514 | 1.1674 | 1
IOMP20260718122004 | Godrej Joka | Civil - Cement |  | 2026-07-18 | 0.0229 | 0.0229 | 1
IOMP20260718123408 | Godrej Joka | Miscellaneous / other works |  | 2026-07-18 | 0.0253 | 0.0253 | 1
IOMP20260718125148 | Godrej Joka | Miscellaneous / other works |  | 2026-07-18 | 0.041 | 0.041 | 1
IOMP20260723193610 | Godrej Joka | Finishing - Tiles |  | 2026-07-23 | 0.1062 | 0.1032 | 1
IOMP20260729173346 | Godrej Joka | MEP - Plumbing and Fire fighting equipments and fittings |  | 2026-07-29 | 0.65 | 0.538 | 1
IOMP20260730121059 | Godrej Joka | Finishing - Tiles |  | 2026-07-30 | 0.1844 | 0.1727 | 1
IOMP20260730205912 | Godrej Joka | Miscellaneous / other works |  | 2026-07-30 | 0.00183 | 0.00183 | 1
IOMP20260730211650 | Godrej Joka | Civil - RMC |  | 2026-07-30 | 1.647 | 1.583 | 1
IOMP20260731201247 | Godrej Joka | MEP - Electrical equipment and fitting |  | 2026-07-31 | 0.0394 | 0.03773 | 1
IOMP20260816164958 | Godrej Joka | Miscellaneous / other works |  | 2026-08-16 | 0.0073 | 0.0073 | 1
IOMP20260816170023 | Godrej Joka | Miscellaneous / other works |  | 2026-08-16 | 0.1368 | 0.0895 | 1
IOMP20260819195811 | Godrej Joka | Civil - Steel Rebar |  | 2026-08-19 | 2.1594 | 1.8844 | 1
IOMP20260826114532 | Godrej Joka | Civil - RMC |  | 2026-08-26 | 0.564 | 0.5499 | 1
IOMP20260415061139 | B L saha | Miscellaneous / other works |  | 2026-04-15 | 0.264 | 0.2508 | 1
IOMP20260415062933 | B L saha | Civil - RMC |  | 2026-04-15 | 29.1854 | 27.5003 | 1
IOMP20260418014929 | B L saha | Civil - RMC |  | 2026-04-18 | 0.5616 | 0.5288 | 1
IOMP20260519102816 | B L saha | Civil - Aluminium Formwork |  | 2026-05-19 | 2.79 | 2.79 | 1
IOMP20260527112827 | B L saha | Civil - Steel Rebar |  | 2026-05-27 | 1.4652 | 1.3517 | 1
IOMP20260622063809 | B L saha | Miscellaneous / other works |  | 2026-06-22 | 0.19 | 0.1793 | 1
IOMP20260708124512 | B L saha | Civil - RMC |  | 2026-07-08 | 0.075 | 0.0678 | 1
IOMP20260709012404 | B L saha | Civil - Steel Rebar |  | 2026-07-09 | 5.1827 | 4.5027 | 1
IOMP20260805170244 | B L saha | Finishing - Tiles |  | 2026-08-05 | 0.74 | 0.71 | 1
IOMP20260507054926 | Godrej Prakriti | Miscellaneous / other works |  | 2026-05-07 | 0.0763 | 0.0763 | 1
IOMP20260604122703 | Godrej Prakriti | Finishing - Tiles |  | 2026-06-04 | 0.0312 | 0.0305 | 1
IOMP20260716110856 | Godrej Prakriti | Finishing - Stones/Marbles |  | 2026-07-16 | 0.0126 | 0.0126 | 1
IOMP20260721202833 | Godrej Prakriti | Civil - Cement |  | 2026-07-21 | 0.0114 | 0.0114 | 1
IOMP20260820212754 | Godrej Prakriti | Civil - Cement |  | 2026-08-20 | 0.0123 | 0.011 | 1
IOMP20260825160839 | Godrej Prakriti | MEP - Plumbing and Fire fighting equipments and fittings |  | 2026-08-25 | 0.0549 | 0.0309 | 1
IOMP20260330114617 | Raipur Plotted 1 | Civil - RMC |  | 2026-03-30 | 0.068 | 0.034 | 1
IOMP20260411021131 | Raipur Plotted 1 | MEP - Plumbing and Fire fighting equipments and fittings |  | 2026-04-11 | 1.4434 | 0.7217 | 1
IOMP20260511020014 | Raipur Plotted 1 | MEP - Plumbing and Fire fighting equipments and fittings |  | 2026-05-11 | 1.434 | 0.717 | 1
IOMP20260526020724 | Raipur Plotted 1 | Civil - Steel Rebar |  | 2026-05-26 | 0.902 | 0.3855 | 1
IOMP20260827120211 | Raipur Plotted 1 | MEP - Plumbing and Fire fighting equipments and fittings |  | 2026-08-27 | 1.07 | 0.5198 | 1
IOMP20260515102526 | Godrej Ushti 1 | Civil - Steel Rebar |  | 2026-05-15 | 0.198 | 0.1859 | 1
IOMP20260515110913 | Godrej Ushti 1 | MEP - Plumbing and Fire fighting equipments and fittings |  | 2026-05-15 | 0.0245 | 0.0217 | 1
IOMP20260519063945 | Godrej Ushti 1 | Civil - RMC |  | 2026-05-19 | 0.54616 | 0.54616 | 1
IOMP20260521070356 | Godrej Ushti 1 | Infrastructure - General |  | 2026-05-21 | 0.3113 | 0.275 | 1
IOMP20260525011828 | Godrej Ushti 1 | Infrastructure - General |  | 2026-05-25 | 0.5391 | 0.4973 | 1
IOMP20260616040959 | Godrej Ushti 1 | Civil - Steel Rebar |  | 2026-06-16 | 0.396 | 0.3509 | 1
IOMP20260629101300 | Godrej Ushti 1 | Miscellaneous / other works |  | 2026-06-29 | 0.0067 | 0.006 | 1
IOMP20260702081120 | Godrej Ushti 1 | Miscellaneous / other works |  | 2026-07-02 | 0.1104 | 0.1045 | 1
IOMP20260808121155 | Godrej Ushti 1 | Civil - RMC |  | 2026-08-08 | 0.0451 | 0.0449 | 1

## Balance
Project | Contract Award Package | Revised Plan Date | Actual/CBE Award Date | Schedule Date | PTE Value (₹ Cr) | BOQ Status | Drawing Status | Currently With | Dependency
Godrej Blue | Windows | 2026-08-22 | 2026-09-11 | 2026-09-11 |  | Provided | Provided | C&P
Godrej Blue | Glass Railing | 2026-09-30 | 2026-09-30 | 2026-09-30 |  | Provided | Provided | C&P
Godrej Blue | Sub station -Core &Shell | 2026-09-07 | 2026-09-07 | 2026-09-07 | 1.34 | Provided | Provided | C&P
Godrej Blue | CP Fittings and Sanitary Fixtures including Kitchen sink | 2026-09-10 | 2026-09-11 | 2026-09-11 | 6.28 | Provided | Provided | C&P
Godrej Blue | External Painting | 2026-09-11 | 2026-09-21 | 2026-09-21 | 4.5 | Provided | Not provided | Design | Design - Drawing
Godrej Blue | Fire Door | 2026-09-15 | 2026-09-15 | 2026-09-15 | 1.67 | Provided | Provided | C&P
Godrej Blue | Internal Electrical | 2026-09-11 | 2026-09-11 | 2026-09-11 | 0.107 | Provided | Provided | C&P
Godrej Blue | Light Fittings | 2026-11-29 | 2026-10-15 | 2026-10-15 | 5 | Not provided | Provided | C&B | C&B - BOQ
Godrej Blue | Louvers for Tower Area | 2026-10-01 | 2026-10-01 | 2026-10-01 | 0.4 | Not provided | Provided | C&B | C&B - BOQ
Godrej Blue | Solar | 2026-12-13 | 2026-12-13 | 2026-12-13 | 1.7 | Provided | Provided | C&P
Godrej Blue | DG | 2026-11-12 | 2026-11-12 | 2026-11-12 |  | Provided | Provided | C&P
Godrej Blue | Play Amenities( Cricket ground, Basket Ball ground, jogging etc.) | 2027-05-03 | 2027-05-03 | 2027-05-03 | 0.65 | Not provided | Provided | C&B | C&B - BOQ
Godrej Blue | Internal Electrical - Panels | 2026-10-12 |  | 2026-10-12 |  | Provided | Provided | C&P
Godrej Blue | Fire Fighting - Pumps | 2026-11-26 | 2026-11-26 | 2026-11-26 | 0.25 | Provided | Provided | C&P
Godrej Blue | Fire Fighting - Panels | 2026-11-26 | 2026-11-26 | 2026-11-26 | 0.067 | Provided | Provided | C&P
Godrej Blue | Expansion Joint | 2026-09-27 | 2026-09-20 | 2026-09-20 | 0.46 | Provided | Provided | C&P
Godrej Blue | External Plumbing - Pumps & Panels | 2026-12-11 | 2026-12-11 | 2026-12-11 | 0.7 | Provided | Provided | C&P
Godrej Blue | External Electrical - Panels | 2026-12-11 | 2026-12-11 | 2026-12-11 |  | Provided | Provided | C&P
Godrej Blue | Hardscape | 2026-10-04 | 2026-10-04 | 2026-10-04 | 2.14 | Not provided | Provided | C&B | C&B - BOQ
Godrej Blue | Softscape-shurbs | 2026-10-04 | 2026-10-04 | 2026-10-04 | 2.5 | Not provided | Provided | C&B | C&B - BOQ
Godrej Blue | Plantation | 2026-09-23 | 2026-09-23 | 2026-09-23 | 1.8 | Provided | Provided | C&P
Godrej Blue | Road | 2026-10-13 | 2026-10-13 | 2026-10-13 | 0.35 | Not provided | Provided | C&B | C&B - BOQ
Godrej Blue | FAPA, CCTV | 2026-10-13 | 2026-10-13 | 2026-10-13 | 3.25 | Provided | Provided | C&P
Godrej Blue | Security, Boom Barriers | 2026-10-13 | 2026-10-13 | 2026-10-13 | 0.75 | Not provided | Provided | C&B | C&B - BOQ
Godrej Blue | External Illumination | 2026-10-13 | 2026-10-13 | 2026-10-13 | 0.85 | Not provided | Not provided | Design | Design - BOQ
Godrej Blue | Club House Core & Shell | 2026-12-01 | 2026-12-01 | 2026-12-01 | 3.07 | Provided | Provided | C&P
Godrej Blue | Louver for Non Tower | 2027-02-01 | 2027-02-01 | 2027-02-01 | 1.5 | Not provided | Not provided | Design | Design - BOQ
Godrej Blue | Timber Structure work for Tree House, Board Walk & Viewing Platform | 2027-03-17 | 2027-03-17 | 2027-03-17 | 1.5 | Not provided | Not provided | Design | Design - BOQ
Godrej Blue | Club House Interiors | 2027-03-23 | 2027-03-23 | 2027-03-23 | 7.22 | Not provided | Provided | C&B | C&B - BOQ
Godrej Se7en, Phase 2A | Panels except High Side | 2026-08-11 | 2026-12-03 | 2026-12-03 | 0.5 | Not provided | Provided | C&B | C&B - BOQ
Godrej Se7en, Phase 2A | DG | 2026-07-17 | 2026-10-15 | 2026-10-15 |  | Provided | Provided | C&P
Godrej Se7en, Phase 2A | External Firefighting | 2026-07-13 | 2026-09-06 | 2026-09-06 |  | Provided | Provided | C&P
Godrej Se7en, Phase 2A | Swimming Pool | 2026-10-13 | 2026-06-24 | 2026-06-24 |  | Provided | Provided | C&P
Godrej Se7en, Phase 2A | Road | 2026-07-11 | 2026-11-21 | 2026-11-21 | 1 | Not provided | Provided | C&B | C&B - BOQ
Godrej Se7en, Phase 2A | Hard Scape Work | 2026-06-28 | 2026-10-13 | 2026-10-13 |  | Provided | Provided | C&P
Godrej Se7en, Phase 2A | Landscape Work | 2026-09-28 | 2026-10-13 | 2026-10-13 |  | Provided | Provided | C&P
Godrej Se7en, Phase 2A | Club House Finishing & Interiors incl MEP & HVAC | 2026-09-21 | 2026-08-06 | 2026-08-06 |  | Provided | Provided | C&P
Godrej Se7en, Phase 2A | FTTH & CCTV, Video Door Phone, Access Control | 2026-04-25 | 2026-11-14 | 2026-11-14 | 0.5 | Not provided | Not provided | Design | Design - BOQ
Godrej Se7en, Phase 2A | SITC Sports flooring | 2026-09-15 | 2026-10-07 | 2026-10-07 |  | Not provided | Provided | C&B | C&B - BOQ
Godrej Se7en, Phase 2A | Soft Furnishing Club House | 2026-09-15 | 2026-10-02 | 2026-10-02 |  | Not provided | Provided | C&B | C&B - BOQ
Godrej Se7en, Phase 2A | Gym Equipment & Play Equipment in Club House | 2026-09-15 | 2026-08-04 | 2026-08-04 |  | Provided | Provided | C&P
Godrej Se7en, Phase 2A | External Illumination | 2026-09-10 | 2026-10-10 | 2026-10-10 | 0.25 | Not provided | Provided | C&B | C&B - BOQ
Godrej Se7en, Phase 2A | External Louver for Non Tower | 2026-10-11 | 2026-08-31 | 2026-08-31 |  | Provided | Provided | C&P
Godrej Se7en, Phase 2A | Sculptures | 2026-10-16 | 2026-11-15 | 2026-11-15 | 0.2 | Not provided | Not provided | Design | Design - BOQ
Godrej Se7en, Phase 2B | Fire Fighting - Panels | 2026-12-21 | 2026-07-13 | 2026-07-13 |  | Provided | Provided | C&P
Godrej Se7en, Phase 2B | External Plumbing - Panels | 2026-10-04 | 2026-07-31 | 2026-07-31 |  | Provided | Provided | C&P
Godrej Se7en, Phase 2B | External Electrical -HT Panel | 2026-09-03 | 2026-12-24 | 2026-12-24 | 1 | Not provided | Not provided | Design | Design - BOQ
Godrej Se7en, Phase 2B | External Electrical - Panels except High Side | 2026-08-05 | 2026-07-31 | 2026-07-31 |  | Not provided | Provided | C&B | C&B - BOQ
Godrej Se7en, Phase 2B | Solar | 2026-08-27 | 2026-09-02 | 2026-09-02 | 0.13 | Provided | Provided | C&P
Godrej Se7en, Phase 2B | DG | 2027-01-13 | 2026-07-01 | 2026-07-01 |  | Provided | Provided | C&P
Godrej Se7en, Phase 2B | Road | 2026-10-12 | 2026-10-28 | 2026-10-28 | 1 | Provided | Provided | C&P
Godrej Se7en, Phase 2B | Hardscape | 2026-10-04 | 2026-10-04 | 2026-10-04 |  | Provided | Provided | C&P
Godrej Se7en, Phase 2B | Softscape | 2026-10-04 | 2026-10-04 | 2026-10-04 |  | Provided | Provided | C&P
Godrej Se7en, Phase 2B | Club House Interiors | 2026-11-09 | 2026-11-09 | 2026-11-09 | 2.4 | Provided | Provided | C&P
Godrej Se7en, Phase 2B | FAPA and CCTV and FTTH, Security, Boom Barriers | 2026-11-15 | 2026-09-12 | 2026-09-12 |  | Provided | Provided | C&P
Godrej Se7en, Phase 2B | Play Amenities | 2026-11-24 | 2026-11-24 | 2026-11-24 | 0.25 | Provided | Provided | C&P
Godrej Se7en, Phase 2B | Children's Play Equipments | 2026-11-24 | 2026-11-24 | 2026-11-24 | 0.15 | Provided | Provided | C&P
Godrej Se7en, Phase 2B | Gym Equipments | 2026-11-24 | 2026-11-24 | 2026-11-24 | 0.07 | Provided | Provided | C&P
Godrej Se7en, Elevate | Internal Plumbing | 2026-07-04 | 2026-09-15 | 2026-09-15 |  | Provided | Provided | C&P
Godrej Se7en, Elevate | CP Fittings and Sanitary Fixtures | 2026-08-31 | 2026-10-23 | 2026-10-23 |  | Provided | Provided | C&P
Godrej Se7en, Elevate | Fire Fighting | 2026-07-19 | 2026-09-03 | 2026-09-03 | 2.9 | Provided | Provided | C&P
Godrej Se7en, Elevate | Fire Fighting - Pumps | 2026-11-29 | 2026-09-03 | 2026-09-03 | 0.3 | Provided | Provided | C&P
Godrej Se7en, Elevate | Fire Fighting - Panels | 2027-01-28 | 2026-09-03 | 2026-09-03 | 0.15 | Provided | Provided | C&P
Godrej Se7en, Elevate | DB, MCB, RCCB | 2027-05-19 | 2026-08-16 | 2026-08-16 |  | Provided | Provided | C&P
Godrej Se7en, Elevate | Internal Electrical - Panels | 2027-08-19 | 2026-09-15 | 2026-09-15 |  | Provided | Provided | C&P
Godrej Se7en, Elevate | Windows, Louvers, FAÇADE and Fins | 2026-08-31 | 2026-11-12 | 2026-11-12 | 4.5 | Provided | Provided | C&P
Godrej Se7en, Elevate | External Painting | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2.4 | Not provided | Not provided | Design | Design - BOQ
Godrej Se7en, Elevate | Lift | 2026-08-11 | 2026-08-11 | 2026-08-11 |  | Provided | Provided | C&P
Godrej Se7en, Elevate | External Plumbing | 2026-12-31 | 2026-09-15 | 2026-09-15 |  | Provided | Provided | C&P
Godrej Se7en, Elevate | External Plumbing - Pumps | 2026-12-15 | 2026-09-15 | 2026-09-15 |  | Provided | Provided | C&P
Godrej Se7en, Elevate | External Plumbing - Panels | 2027-02-13 | 2026-09-15 | 2026-09-15 |  | Provided | Provided | C&P
Godrej Se7en, Elevate | External Electrical | 2026-12-31 | 2026-09-15 | 2026-09-15 | 1.5 | Provided | Provided | C&P
Godrej Se7en, Elevate | External Electrical - Panels | 2026-12-15 | 2026-09-15 | 2026-09-15 | 1 | Provided | Provided | C&P
Godrej Se7en, Elevate | Solar | 2026-11-12 | 2026-11-12 | 2026-11-12 | 0.12 | Provided | Provided | C&P
Godrej Se7en, Elevate | DG | 2027-06-20 | 2026-09-15 | 2026-09-15 | 1.4 | Not provided | Provided | C&B | C&B - BOQ
Godrej Se7en, Elevate | Road | 2027-02-28 | 2027-02-28 | 2027-02-28 | 1.5 | Not provided | Not provided | Design | Design - BOQ
Godrej Se7en, Elevate | Hardscape | 2027-03-05 | 2027-03-05 | 2027-03-05 | 0.7 | Not provided | Not provided | Design | Design - BOQ
Godrej Se7en, Elevate | Softscape | 2027-03-05 | 2027-03-05 | 2027-03-05 | 0.4 | Not provided | Not provided | Design | Design - BOQ
Godrej Se7en, Elevate | Club House Interiors | 2027-02-18 | 2027-02-18 | 2027-02-18 | 2 | Not provided | Not provided | Design | Design - BOQ
Godrej Se7en, Elevate | HVAC Package | 2027-02-18 | 2026-10-02 | 2026-10-02 |  | Provided | Provided | C&P
Godrej Se7en, Elevate | FAPA and CCTV and FTTH, Security, Boom Barriers | 2027-02-18 | 2026-09-17 | 2026-09-17 |  | Provided | Provided | C&P
Godrej Se7en, Elevate | Play Amenities | 2027-02-18 | 2027-02-18 | 2027-02-18 | 0.25 | Not provided | Not provided | Design | Design - BOQ
Godrej Se7en, Elevate | Children's Play Equipments | 2027-02-18 | 2027-02-18 | 2027-02-18 | 0.15 | Not provided | Not provided | Design | Design - BOQ
Godrej Se7en, Elevate | Gym Equipments | 2027-02-18 | 2027-02-18 | 2027-02-18 | 0.07 | Not provided | Not provided | Design | Design - BOQ
Plotted Development at Usthi | New Culvert Construction | 2026-06-30 | 2026-06-30 | 2026-06-30 |  | provided | Provided | C&P
Plotted Development at Usthi | Irrigation Work | 2026-07-23 | 2026-07-23 | 2026-07-23 |  | Not provided | Provided | C&B | C&B - BOQ
Plotted Development at Usthi | Club House - Door & Window Package | 2026-08-10 | 2026-08-10 | 2026-08-10 |  | Provided | Provided | C&B
Plotted Development at Usthi | Club House - External Paint | 2026-08-10 | 2026-08-10 | 2026-08-10 |  | Provided | Provided | C&P
Plotted Development at Usthi | Club House - Interior with Furniture | 2026-08-02 | 2026-08-02 | 2026-08-02 |  | Not provided | Provided | C&B | C&B - BOQ
Plotted Development at Usthi | Club House - HVAC | 2026-07-31 | 2026-07-31 | 2026-07-31 |  | provided | provided | C&P
Plotted Development at Usthi | Banquate - External Paint | 2026-07-03 | 2026-07-03 | 2026-07-03 |  | Provided | Provided | C&P
Plotted Development at Usthi | Banquate - Interior with Furniture | 2026-08-02 | 2026-08-02 | 2026-08-02 |  | Not provided | Provided | C&B | C&B - BOQ
Raipur Plotted | LANDSCAPE- Softscape | 2026-06-16 | 2026-10-13 | 2026-10-13 |  | Not provided | NOT PROVIDED | Design | Design - BOQ
Raipur Plotted | LANDSCAPE- Hardscape | 2026-06-16 | 2026-10-04 | 2026-10-04 |  | Not provided | Provided | C&B | C&B - BOQ
Raipur Plotted | Club House - Interior | 2026-10-16 | 2026-09-08 | 2026-09-08 |  | Provided | Provided | C&P